## PIXMAMA
SL | Project Code | Project Name | LLD LOCKED | Status | Dependency | Comment | Expected Timeline
1 | SOC01 | Alarm Correlation and trigger first time right stakeholder | Yes | WIP | All cleared | omi will support for | TBA
2 | SOC02 | KPI Dashboard (Radio, Core, TX domain) Node level/Region wise/Nationwide | Yes | Not Started | All cleared | Not Started | WIP
3 | SOC03 | MPBN link Failure / GE down auto incident Notification | No | Not Started | LLD required | omi will share LLD by 16/1/2021 | TBA
4 | SOC04 | Mobile App/ Push-Pull SMS for site status (up/down, KPI, current alarms, history alarms, BB status, Down aging) checking remotely | NA | Delivered | NA | Completed | NA
5 | SOC05 | RBSID Check between NodeB and RNC/RRU Power check | Yes | Not Started | All cleared | Project Reconciliation (Mustafiz vai and mustahid vai) | TBA
6 | SOC06 | Service/KPI degradation auto notification (SMS/Mail) (PSA) | Yes | WIP | All cleared | UAT Pending | 2020-02-15
7 | SOC07 | Site (Multi Tech.) status checking for Node level | Yes | WIP | All cleared | UAT Pending | 2021-01-30
8 | SOC08 | Whole Network/ NE/Node Summary/ Inventory Hierarchy | No | Not Started | Arif(CN), Omi(soc), Rupon da(digital), Rafsan(oss) | required settlement upon discussion by timeline (possible droped item ) | 2021-01-25
9 | SOC09 | Auto Back up (Node level) | No | Not Started | Arif(CN), Omi(soc), Rupon da(digital), Rafsan(oss) | required settlement upon discussion by timeline (possible droped item) | 2021-01-12
10 | SOC10 | Site/Cell Outage aging dashboard | NA | Delivered | NA | Completed | NA
11 | SOC12 | Change(CR) Correlation with Service/KPI degradation | Yes | Not Started | OSS for remedy API | @Hosny, OSS | 2021-02-28
12 | SOC14 | Incident notification merging with incident Tracker and Mobireach platform ( SMS sending plantform ) | Yes | WIP | NA | paritial developed item handed over to pixmama for enhanment | TBA
13 | SOC15 | Network Quality Dashboard | Yes | WIP | All c;leared | WIP | 2021-01-15
14 | SOC16 | Network Fault Dashboard | Yes | Delivered | NA | Completed | 2020-12-30
15 | SOC17 | SOC BOT | No | Not Started | omi & pixmama | paritial developed item will be handedove | 2021-03-15
16 | SOC20 | No Click RPA Periodic Notification | NA | HO Project | program hosted on VM and dicssussion done | Final UAT Sign WIP | 2021-01-08
17 | SOC21 | Critical & Corporate site RPA Notification | NA | HO Project | program hosted on VM and dicssussion done | Final UAT Sign WIP | 2021-01-08
18 | SOC22 | Smart Eye (Priority Site Down Escalation) | NA | HO Project | NA | pending discussed and HO process | 2021-01-28
19 | SOC23 | Auto NTTN Escalation (RPA) | NA | HO Project | NA | pending discussed and HO process | 2021-02-28
20 | SOC24 | ComboRaid : FTT Handler | NA | HO Project | program hosted on VM and dicssussion done | Final UAT Sign WIP | 2021-01-13
21 | SOC26 | NCR Analyzer | NA | HO Project | NA | pending discussed and HO process | 2021-01-28
22 | SOC27 | Outage Settlement (RCA Analyzer) | NA | HO Project | NA | pending discussed and HO process | 2021-01-23
23 | SOC28 | DC Low/Site Down BOT | NA | HO Project | program hosted on VM and dicssussion done | Final UAT Sign WIP | 2021-01-17
24 | SOC29 | Hunter: Long Outage (as-is) | NA | Delivered | NA | Completed | NA
25 | SOC30 | DGtor: DG site outage analyser | NA | Not Started | NA | pending discussed and HO process | 2021-01-29
26 | SOC34 | NTTN POP site Power | No | Not Started | LLD required | pending disscussion | NA
27 | SOC35 | AI incident Notification | NA | Handed Over | NA | Completed | NA
28 | SOC36 | IIG Traffic Auto Notification | NA | HO Project | shakila(planning,technology) | pending discussed and HO process | 2021-02-28